## Simple Gantt chart
Task | Start date | End date | Phases | Start date | End date
Project Plan | 2022-09-08 | 2022-09-29 | Documentation | 2022-08-29 | 2022-09-16
User Stories | 2022-08-31 | 2022-09-10 | Design | 2022-05-15 | 2022-05-24
UML Diagram | 2022-09-29 | 2022-12-16 | Implementing | 2022-05-25 | 2022-06-04
Test Plan | 2022-09-09 | 2022-09-15 | Testing | 2022-06-05 | 2022-06-07
Design Document | 2022-09-08 | 2022-12-16
Prototype Iteration | 2022-10-07 | 2022-11-04 | Milestones | Deliverables
Release Version | 2022-11-25 | 2022-12-16 | Documentation | Project Plan, User Stories, Test Plan, Design Documentation, UML Diagram
Design Frontend | 2022-09-23 | 2022-12-16 | Design | Datebase Design, Website Design
|  |  | Implementing | Java Application, React Application
Task | Start on day | Duration
Project Plan | 8 | 21
User Stories | 0 | 10
UML Diagram | 23 | 78
Test Plan | 9 | 6
Design Document | 8 | 99
Prototype Iteration | 37 | 28
Release Version | 86 | 21
Design Frontend | 23 | 84
Planning
Sprint 1 | Project Plan, User Stories, Test Plan, Design Document, Implementing Course Bundles
Sprint 2 | Version 1 Design Document, 1st Prototype Iteration, Reschearch Document, Implementing Bundle Packages and Accounts (optional Teachers), Design Frontend
Sprint 3 | Version 2 Design Document, Quality assurance in Git using SonarQube, Test Strategy, 2nd Prototype Iteration
Sprint 4 | Version 3 Design Document, 1st Release Version, UX Feedback Report
Sprint 5 | Final design document, Security report , 2nd release version, Up-to-date product and sprint backlogs and burn-down charts, Websockets
Sprint 6 | Final Assessment

## Gantt chart with dependencies
Task | Dependency | Duration (Days) | Team | Owner | Task Start Date | Task End Date | Dep Start Date | Dep End Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Task 1 |  | 5 |  |  | 2021-08-05 | 2021-08-10 | N/A | N/A | bar: 5 to 10
Task 2 | Task 1 | 2 |  |  | 2021-08-10 | 2021-08-12 | 2021-08-05 | 2021-08-10 | bar: 10 to 12
Task 3 | Task 2 | 3 |  |  | 2021-08-12 | 2021-08-15 | 2021-08-10 | 2021-08-12 | bar: 12 to 15
Task 4 | Task 3 | 4 |  |  | 2021-08-15 | 2021-08-19 | 2021-08-12 | 2021-08-15 | bar: 15 to 19
Task 5 | Task 4 | 4 |  |  | 2021-08-19 | 2021-08-23 | 2021-08-15 | 2021-08-19 | bar: 19 to 23
Task 6 | Task 5 | 1 |  |  | 2021-08-23 | 2021-08-24 | 2021-08-19 | 2021-08-23 | bar: 23 to 24
Task 7 | Task 6 | 1 |  |  | 2021-08-24 | 2021-08-25 | 2021-08-23 | 2021-08-24 | bar: 24 to 25
Task 8 | Task 7 | 2 |  |  | 2021-08-25 | 2021-08-27 | 2021-08-24 | 2021-08-25 | bar: 25 to 27
Task 9 | Task 8 | 1 |  |  | 2021-08-27 | 2021-08-28 | 2021-08-25 | 2021-08-27 | bar: 27 to 28
Task 10 | Task 9 | 2 |  |  | 2021-08-28 | 2021-08-30 | 2021-08-27 | 2021-08-28 | bar: 28 to 30
Task 11 | Task 10 | 1 |  |  | 2021-08-30 | 2021-08-31 | 2021-08-28 | 2021-08-30 | bar: 30
Note on F2: Edit this date manually to have all other task start and end dates recalculate in a "cascading" fashion.